## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Unavailability of a Professional Networking Platform for Higher Education Students for Continuous Professional Development.
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2025-09-19
EXPECTED COMPLETION DATE
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To develop a **professional networking platform for higher education students** to connect, share skills, and explore career opportunities.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | To provide a dedicated platform for students to build professional networks, improve skills, and access career opportunities.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | **Goals (in short):** * Build a student professional networking platform * Enable profile creation and connections * Share projects, skills, and opportunities
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | **Expected Deliverables (in short):** * Functional web application * Student networking platform * Project documentation and source code
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | **Within Scope:** User registration, login, profile creation, networking, and posting updates.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | **Outside Scope:** Mobile app development, paid services, and third-party job portal integrations.
PROJECT RESOURCES AND COSTS+A18:B37
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Full-Stack Developer (Student)
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop/PC, Internet Connection, GitHub, VS Code, MongoDB Database
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Development Tools – Free (Open Source) Cloud/Hosting – Free Tier (AWS / MongoDB Atlas) Total Estimated Cost – Minimal / $0 (Student Project)
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | saish shaikh
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | **Key Stakeholders:** * Cloud Counselage Pvt. Ltd. * Project Mentor * **Saish Shaikh** (Student Developer) * Higher Education Students (Platform Users)
END CUSTOMER (Mention the client name.) | Higher Education Students and Early Career Professionals RISKS
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Possible server downtime or hosting issues Data privacy and security risks Limited development time for completing all features Low initial user adoption of the platform
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Users will have stable internet access Students are interested in networking and career development Open-source tools and MERN stack will be sufficient for development
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Project must be completed within the internship timeline Development limited to MERN stack technologies Budget constraints (using mostly free/open-source tools)
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 09-25-2025
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 2025-02-10
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 11-20-2025
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 11-25-2025
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 11-20-2025
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 11-25-2025
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 11-30-2025