## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2024 - Data Analytics Project Schedule
|  | PROJECT START DATE | 2025-09-19
|  | Display Week Sr No | 1 | [10 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13 | [6 empty] | 2025-10-20 | [6 empty] | 2025-10-27 | [6 empty] | 2025-11-03 | [6 empty] | 2025-11-10
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2025-09-15 to 2025-11-16
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2025-09-15 to 2025-11-16
1 | Phase - 1
1.1 | Week 1 | Requirement Gathering | Understanding Project Requirements | Meeting with stakeholders, defining project objectives, identify target user | None | Saish Shaikh | 2025-09-19 | 2025-09-26 | 2025-09-27 | 12 | Completed | 100 | Project requirements clearly defined and documented.
1.2 | Week 2 | System Planning & Feasibility | Project Planning | Technical feasibility analysis,Decide tech stack,Cost & time estimation | Requirements defined | Saish Shaikh | 2025-09-28 | 2025-10-03 | 2025-10-04 | 10 | Completed | 100 | Tech stack selected and project timeline finalized.
1.3 | Week 3 | System Architecture Design | Designing Architecture | Define client-server architecture, API structure planning,Database schema design | Planning completed | Saish Shaikh | 2025-10-05 | 2025-10-15 | 2025-10-16 | 15 | Completed | 100 | System architecture and database schema successfully designed.
1.4 | Week 4 | UI/UX Design | Designing User Interface | Wireframing,User flow design,Responsive design planning | Architecture design | Saish Shaikh | 2025-10-17 | 2025-10-27 | 2025-10-28 | 18 | Completed | 100 | Wireframes and user interface design completed.
1.5 | Week 5 | Frontend Setup | Project Initialization | Setup React / Angular / Vue project,Folder structure,Install required libraries | UI design completed | Saish Shaikh | 2025-10-29 | 2025-11-02 | 2025-11-03 | 8 | Completed | 100 | Frontend environment configured successfully.
2 | Phase - 2
2.1 | Week 6 | Core UI Development | Developing Pages | Login & Registration page, Dashboard, Forms & validation, API integration |  | Saish Shaikh | 2025-11-04 | 2025-11-18 | 2025-11-19 | 30 | Completed | 100 | Core frontend pages developed and integrated.
2.2 | Week 7 | Backend Setup | Server Initialization | Setup Node.js / Django / Spring Boot, Configure Express / REST APIs, Connect database, Environment configuration | Architecture design | Saish Shaikh | 2025-11-20 | 2025-11-27 | 2025-11-28 | 12 | Completed | 100 | Backend server configured and connected to database.
2.2 | Week 8 | API Development | CRUD Operations | User authentication (JWT), Create, Read, Update, Delete APIs, Middleware implementation, Error handling | Backend setup | Saish Shaikh | 2025-11-29 | 2025-12-15 | 2025-12-16 | 35 | Completed | 100 | CRUD APIs and authentication implemented successfully.
2.3 | Week 9 | Database Implementation | Database Development | Create tables/collections, Define relationships, Implement indexing, Data validation rules | API structure | Saish Shaikh | 2025-12-17 | 2025-12-26 | 2025-12-27 | 15 | Completed | 100 | Database structure created and integrated with backend.
2.4 | Week 10 | Frontend & Backend Integration | System Integration | Connect frontend with APIs, Test API responses, Debug integration errors, Authentication flow testing | Frontend & Backend completed | Saish Shaikh | 2025-12-28 | 2026-01-06 | 2026-01-07 | 18 | Completed | 100 | Frontend and backend successfully connected.
2.5 | Week 11 | Testing | System Testing | Unit testing, Integration testing, UI testing, Fix bugs, Performance testing | Integration complete | Saish Shaikh | 2026-01-08 | 2026-01-19 | 2026-01-20 | 25 | Completed | 100 | Application tested and major issues resolved.
2.6 | Week 12 | Deployment Setup | Hosting & Deployment | Prepare production build, Deploy frontend (Vercel / Netlify), Deploy backend (Render / AWS / Railway), Setup domain & SSL | Testing completed | Saish Shaikh | 2026-01-20 | 2026-01-27 | 2026-01-28 | 10 | Completed | 100 | Application deployed successfully to production environment.
2.7 | Week 13 | Documentation | Project Documentation | Prepare technical documentation, API documentation, User manual, Project report | Deployment complete | Saish Shaikh | 2026-01-29 | 2026-02-10 | 2026-02-11 | 12 | Completed | 100 | Project documentation completed and submitted.
2.8 | Week 14 | Maintenance | Monitoring & Updates | Monitor server performance, Fix bugs, Add new features, Security updates | Live Project | Saish Shaikh | 2026-02-12 | 2026-02-26 | 2026-02-27 | 10 | Completed | 100 | System monitoring and updates ongoing.
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Data-Driven Analysis of Student Success Factors |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Data analysis report on student attendance and success factors.
PROJECT SCOPE | Focuses on analyzing student attendance data across various events
PROJECT START DATE | 2024-08-24
PROJECT END DATE | 2024-10-08
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 | Initiation | Jishan Attar | 2024-08-24 | 2024-08-28
1.1 | Requirement Gathering | Jishan Attar | 2024-08-24 | 2024-08-28 | 5 | COMPLETED
1.2 | Identify business problem | Jishan Attar | 2024-08-24 | 2024-08-24 | 1 | COMPLETED
1.3 | Recruit a team | Jishan Attar | 2024-08-25 | 2024-08-26 | 2 | COMPLETED
1.4 | Create a project charter | Jishan Attar | 2024-08-27 | 2024-08-27 | 1 | COMPLETED
1.5 | Requirement gathering | Jishan Attar | 2024-08-28 | 2024-08-28 | 1 | COMPLETED
2 | Data Collection | Jishan Attar | 2024-08-30 | 2024-09-03 | 5 | COMPLETED
2.1 | Collecting data (student GPA, Python experience, family income) | Jishan Attar | 2024-08-30 | 2024-09-03 | 5 | COMPLETED
3 | Data Cleaning | Jishan Attar | 2024-09-04 | 2024-09-12 | 9 | COMPLETED
3.1 | Handle missing values | Jishan Attar | 2024-09-04 | 2024-09-06 | 3 | COMPLETED
3.2 | Remove irrelevant data | Jishan Attar | 2024-09-07 | 2024-09-08 | 2 | COMPLETED
3.3 | Normalize/Format data | Jishan Attar | 2024-09-09 | 2024-09-12 | 4 | COMPLETED
4 | Data Analysis | Jishan Attar | 2024-09-13 | 2024-09-23 | 11 | COMPLETED
4.1 | Descriptive statistics | Jishan Attar | 2024-09-13 | 2024-09-14 | 2 | COMPLETED
4.2 | Correlation analysis | Jishan Attar | 2024-09-15 | 2024-09-17 | 3 | COMPLETED
4.3 | Outlier detection | Jishan Attar | 2024-09-18 | 2024-09-19 | 2 | COMPLETED
4.4 | Data visualization | Jishan Attar | 2024-09-20 | 2024-09-23 | 4 | COMPLETED
5 | Insights Generation | Jishan Attar | 2024-09-24 | 2024-10-01 | 8 | COMPLETED
5.1 | Identifying trends and insights | Jishan Attar | 2024-09-24 | 2024-10-01 | 8 | COMPLETED
6 | Report Preparation | Jishan Attar | 2024-10-02 | 2024-10-05 | 4 | COMPLETED
6.1 | Writing the report | Jishan Attar | 2024-10-02 | 2024-10-04 | 3 | COMPLETED
6.2 | Creating visualizations | Jishan Attar | 2024-10-04 | 2024-10-05 | 1 | COMPLETED
7 | Final Review & Submission | Jishan Attar | 2024-10-06 | 2024-10-08 | 3 | COMPLETED
7.1 | Final review and revisions | Jishan Attar | 2024-10-06 | 2024-10-07 | 2 | COMPLETED
7.2 | Submission to stakeholders | Jishan Attar | 2024-10-07 | 2024-10-08 | 1 | COMPLETED
4
3
|  |  | 2020-01-03 | 2020-09-03 | 8
|  |  | 2020-10-03 | 15/3/2020 | 5
|  |  | 16/3/2020 | 22/3/2020 | 7
|  |  | 25/03/2020 | 31/3/2020 | 6
|  |  | 2020-01-04 | 2020-01-04 | 1